# Department of Computer Science & Engineering

National Institute of Technology Rourkela

Research Plan for Capstone Project-I (CS4095)

Autumn Semester 2026-27

# 1. Student Details

| Name of the Candidate | Vineet Nakra |
| --- | --- |
| Registration Number | 123CS0193 |
| Supervisor(s) Name(s) | Prof. Sanjeev Patel |
| Tentative Title of the Research Project | Optimized Multi-Dimensional Attention Spiking Neural Network for Breast Cancer Detection from Histopathology Images |

# 2. Brief Problem Statement

Breast cancer remains one of the leading causes of cancer-related mortality among women worldwide, and early, accurate diagnosis is critical to improving survival outcomes. Histopathological examination of biopsied breast tissue remains the clinical gold standard for distinguishing benign from malignant tumors, but manual examination by pathologists is time-consuming, subject to inter-observer variability, and does not scale well against rising caseloads. Computer-Aided Diagnosis (CAD) systems built on deep learning have shown strong potential to assist pathologists by automating the classification of histopathological images, improving both consistency and throughput.

Recent literature has explored a range of deep learning architectures for this task, from convolutional neural networks combined with gradient-boosted classifiers to attention-augmented networks and transfer-learning-based pipelines. A recent direction, and the specific focus of this capstone project, involves Spiking Neural Networks (SNNs) — class of models that encode information in discrete temporal spikes rather than continuous activations, offering potential energy-efficiency advantages relevant to future deployment on neuromorphic or edge hardware. Satheeshkumar et al. (2026) proposed one such architecture, MASNN-BCD-HI, which combines a Trainable Self-Guided Filter (TSGF) for preprocessing, a Multi-Dimensional Attention Spiking Neural Network (MASNN) that applies spatial, channel, and temporal attention to spiking feature maps, and an Optimization Algorithm for weight tuning, reporting strong benign/malignant classification performance on the BreakHis histopathology dataset.

This project will (a) faithfully reproduce the MASNN-BCD-HI pipeline on the BreakHis dataset with rigorous methodology (patient-wise data splitting to prevent leakage, verified against the paper's published dataset statistics), and (b) conduct a systematic ablation study — training and evaluating variants with each component selectively removed or substituted (e.g., MASNN without TSGF, without attention, and without optimisation algorithm) — to quantify each component's individual contribution to classification performance. The outcome will be both a working, benchmarked reproduction of a recent SNN-based medical imaging architecture, and original empirical evidence clarifying which of its components are load-bearing, contributing a more rigorous understanding than the original publication provides.

# 3. Objectives for Autumn Semester 2026-27

- Complete a focused literature review on spiking neural networks, attention mechanisms, and metaheuristic optimization algorithms in medical image analysis.

- Acquire and verify the BreakHis histopathology dataset, and construct a patient-wise train/validation/test split matching the original paper's reported statistics.

- Implement and validate the Trainable Self-Guided Filter (TSGF) preprocessing module.

- Implement the Multi-Dimensional Attention Spiking Neural Network (MASNN), including spiking convolutional layers, spatial/channel/temporal attention blocks, and a spiking recurrent output stage.

- Implement the Shrike Optimization Algorithm (SOA) and integrate it for MASNN weight optimization.

- Conduct a systematic ablation study isolating the individual contribution of TSGF, attention, and SOA to overall classification performance.

- Benchmark the reproduced model against baseline methods (DNN+gradient-boosting, resolution-adaptive network, CNN+transfer-learning) using accuracy, precision, recall, specificity, F1-score, and ROC-AUC.

- Compile a comprehensive Capstone Project-I report documenting methodology, results, and critical evaluation of the original publication.

# 4. Detailed Month-wise Work Plan (August–November 2026)

| Month | Focus Area | Key Tasks |
| --- | --- | --- |
| August 2026 | Foundations & Preprocessing | Literature review; environment setup (PyTorch, snnTorch); BreakHis acquisition and verification against published statistics; patient-wise data split with leakage verification; TSGF preprocessing module implemented and validated; baseline CNN (TSGF + standard CNN) as reference point. (Work substantially underway at time of submission.) |
| September 2026 | Spiking Neural Networks | Study of LIF neuron model, rate encoding, and surrogate gradients; implementation of spiking convolutional layers (snnTorch); initial spiking classifier developed and evaluated against the CNN baseline. |
| October 2026 | Attention, Full MASNN & SOA | Implementation of spatial/channel/temporal attention block; spiking recurrent layer and full MASNN assembly; Shrike Optimization Algorithm implemented from first principles and integrated with MASNN training. Mid-semester milestone at month end. |
| November 2026 | Ablation Study & Reporting | Design and execution of ablation study (TSGF on/off, attention on/off, SOA vs. standard optimizer); full benchmark evaluation against baseline methods; results compilation; final report drafting and presentation preparation. Final milestone before examination. |

# 5. Expected Deliverables by November 2026

- A fully reproduced and validated MASNN-BCD-HI pipeline (TSGF + MASNN + SOA) trained and evaluated on the BreakHis dataset..

- A comparative benchmark against baseline methods reported in the literature (accuracy, precision, recall, specificity, F1-score, ROC-AUC).

- A complete, documented, and reusable codebase, positioned for extension in Capstone Project-II.

- A comprehensive written report suitable for panel evaluation.

# 6. Milestones and Evaluation Points

| Mid-Semester Milestone (end of October 2026) | Full MASNN + SOA pipeline implemented, trained, and producing preliminary results; ablation study design finalized. |
| --- | --- |
| Final Milestone (November 2026, before final examination) | Ablation study complete; full benchmark evaluation complete; final report and presentation ready for panel evaluation. |

# 7. Supervisor's Recommendation

“The proposed research plan is realistic, well-structured, and recommended for implementation during Autumn Semester 2026-27.”

Signature of Supervisor: ______________________________

Name: Prof. Sanjeev Patel

Designation: ______________________________

Date: ______________________________